## 13-04-2015
Date | Bugzilla Ticket No | Artifacts Name (with full Path) | Comments (What was changed and need to be tested) | Developer | Require Database | SQL | Deployed using delta (Yes/No) | How is done by Developer (Explain in detail)
2015-05-28 |  | EJBServer\components\MOLSA\source\curam\molsa\ip\sl\impl\MOLSAMaintainInformationProvider.java webclient\components\MOLSA\InformationProvider\MOLSA_createInformationRequest1.uim | Changed the IP page to display Case participants not just case members | Smitha | No |  |  | Need to do builds as class file and UIM is changed
2015-08-20 |  | The database field type has been changed to CLOB for IDTABBEDLIST as the bulk sms was not working for more than 500 | Test the bulk sms | Ditto | Yes | The database field type has been changed to CLOB for IDTABBEDLIST as the bulk sms was not working for more than 500 ALTER TABLE MOLSASMSWMINSTANCE ADD IDTABBEDLIST1 CLOB; update MOLSASMSWMINSTANCE set IDTABBEDLIST1=IDTABBEDLIST; ALTER TABLE MOLSASMSWMINSTANCE drop column IDTABBEDLIST ; ALTER TABLE MOLSASMSWMINSTANCE rename column IDTABBEDLIST1 to IDTABBEDLIST; |  | New ear and SQL
2015-08-20 |  | IP Request is not saving the details of who created it | Test the IP Request Page | Ditto | Yes | ALTER TABLE MOLSAInformationRequest ADD createdByvarchar2(64); |  | New ear and SQL