## 02-21-2017
Date | Bugzilla Ticket No | Artifacts Name (with full Path) | Comments (What was changed and need to be tested) | Developer | Require Database | SQL | Deployed using delta (Yes/No) | How is done by Developer (Explain in detail)
2017-02-15 |  | /EJBServer/project/properties/Bootstrap.properties /EJBServer/components/MOLSA/properties/Application.prx /Curam/components/MOLSA/CDEJResources.properties /Curam/components/MOLSA_ar/CDEJResources.properties | CR 8.1 Date Format Display | Bhaskar | Yes |  |  | Note: New entry is added and modified existing entry in applicattion.prx file, require build insertproperties
2017-02-21 |  | New Files Added \EJBServer\components\MOLSA\codetable\CT_MOLSACertPeriodCode.ctx \EJBServer\components\MOLSA\model\Packages\ProductDelivery\Certification\Facade.efx \EJBServer\components\MOLSA\model\Packages\Domain Definition\ProductDelivery.efx \EJBServer\components\MOLSA\model\Packages\ProductDelivery\Certification\Batch.efx \EJBServer\components\MOLSA\source\curam\molsa\pd \EJBServer\components\MOLSA\source\curam\molsa\pd\batch \EJBServer\components\MOLSA\source\curam\molsa\pd\batch\impl \EJBServer\components\MOLSA\source\curam\molsa\pd\batch\impl\MOLSAExpCertCloseCaseBatch.java \EJBServer\components\MOLSA\source\curam\molsa\pd\batch\impl\MOLSAExpCertCloseCaseBatchStream.java \EJBServer\components\MOLSA\source\curam\molsa\pd\batch\impl\MOLSAExpCertCloseCaseBatchStreamWrapper.java \EJBServer\components\MOLSA\source\curam\molsa\pd\batch\impl\MOLSAExpCertCloseCaseBatchWrapper.java \EJBServer\components\MOLSA\source\curam\molsa\pd\batch\impl\MOLSAExpCertSuspendCaseBatch.java \EJBServer\components\MOLSA\source\curam\molsa\pd\batch\impl\MOLSAExpCertSuspendCaseBatchStream.java \EJBServer\components\MOLSA\source\curam\molsa\pd\batch\impl\MOLSAExpCertSuspendCaseBatchStreamWrapper.java \EJBServer\components\MOLSA\source\curam\molsa\pd\batch\impl\MOLSAExpCertSuspendCaseBatchWrapper.java \EJBServer\components\MOLSA\source\curam\molsa\pd\facade \EJBServer\components\MOLSA\source\curam\molsa\pd\facade\impl \EJBServer\components\MOLSA\source\curam\molsa\pd\facade\impl\MOLSACalcCertDateRange.java \webclient\components\MOLSA\ReferenceApp\core\Product Delivery\Certification\ProductDelivery_createCertificationView.properties \webclient\components\MOLSA\ReferenceApp\core\Product Delivery\Certification\ProductDelivery_resolveCertification.uim \webclient\components\MOLSA\WebContent\CDEJ\MOLSACertPeriodSelection.js Existing Files Modified \EJBServer\components\MOLSA\clientapps\CommonFilesForCaseView\DefaultProductDeliveryMenu.mnu \EJBServer\components\MOLSA\codetable\CT_BatchProcessName.ctx \EJBServer\components\MOLSA\codetable\CT_CaseCloseReason.ctx \EJBServer\components\MOLSA\codetable\CT_CaseSuspendReason.ctx \EJBServer\components\MOLSA\model\Packages\Domain Definition\Domain Definition.efx \EJBServer\components\MOLSA\model\Packages\ProductDelivery\Certification\Certification.efx \EJBServer\components\MOLSA\model\Packages\ProductDelivery\ProductDelivery.efx \EJBServer\components\MOLSA\model\Packages\Reference Model\Core.efx \EJBServer\components\MOLSA\model\Packages\Reference Model\PDCApproval.efx \EJBServer\components\MOLSA\properties\Application.prx \EJBServer\components\MOLSA\source\curam\molsa\casemanagement\tab\impl\MOLSACaseMenuLoader.java \EJBServer\components\MOLSA\source\curam\molsa\core\facade\impl\MOLSAProductDelivery.java \webclient\components\MOLSA\ReferenceApp\core\Product Delivery\Certification\ProductDelivery_createCertificationView.vim | CR 2.1 Certification Date Changes | Bhaskar | Yes | INSERT INTO CodeTableItem (TABLENAME, CODE, DESCRIPTION, ANNOTATION, COMMENTS, ISENABLED, SORTORDER, LOCALEIDENTIFIER, LASTWRITTEN, VERSIONNO) VALUES ('CaseSuspendReason', 'CSR17002', 'Certification Expired', '', '', '1', 0, 'en', CURRENT TIMESTAMP, 1); INSERT INTO CodeTableItem (TABLENAME, CODE, DESCRIPTION, ANNOTATION, COMMENTS, ISENABLED, SORTORDER, LOCALEIDENTIFIER, LASTWRITTEN, VERSIONNO) VALUES ('CaseCloseReason', 'CC17007', 'Certification Expired', '', '', '1', 0, 'en', CURRENT TIMESTAMP, 1); INSERT INTO CodeTableItem (TABLENAME, CODE, DESCRIPTION, ANNOTATION, COMMENTS, ISENABLED, SORTORDER, LOCALEIDENTIFIER, LASTWRITTEN, VERSIONNO) VALUES ('BatchProcessChunkName', 'BPN17007', 'MOLSA Expired Certification Suspend Case Batch', '', '', '1', 1, 'en', CURRENT TIMESTAMP, 1); INSERT INTO CodeTableItem (TABLENAME, CODE, DESCRIPTION, ANNOTATION, COMMENTS, ISENABLED, SORTORDER, LOCALEIDENTIFIER, LASTWRITTEN, VERSIONNO) VALUES ('BatchProcessChunkName', 'BPN17008', 'MOLSA Expired Certification Close Case Batch', '', '', '1', 1, 'en', CURRENT TIMESTAMP, 1); INSERT INTO CodeTableHeader (TableName, TimeEntered, DefaultCode, LASTWRITTEN, VERSIONNO) VALUES ('MOLSACertPeriodCode', CURRENT TIMESTAMP, 'CPC17003', CURRENT TIMESTAMP, 1); INSERT INTO CTDISPLAYNAME (TableName, LOCALEIdentifier,TEXT,LASTWRITTEN ) VALUES ( 'MOLSACertPeriodCode','en','Certification Period Code', CURRENT TIMESTAMP); INSERT INTO CodeTableItem (TABLENAME, CODE, DESCRIPTION, ANNOTATION, COMMENTS, ISENABLED, SORTORDER, LOCALEIDENTIFIER, LASTWRITTEN, VERSIONNO) VALUES ('MOLSACertPeriodCode', 'CPC17003', 'Three Months', '', '', '1', 0, 'en', CURRENT TIMESTAMP, 1); INSERT INTO CodeTableItem (TABLENAME, CODE, DESCRIPTION, ANNOTATION, COMMENTS, ISENABLED, SORTORDER, LOCALEIDENTIFIER, LASTWRITTEN, VERSIONNO) VALUES ('MOLSACertPeriodCode', 'CPC17006', 'Six Months', '', '', '1', 0, 'en', CURRENT TIMESTAMP, 1); INSERT INTO CodeTableItem (TABLENAME, CODE, DESCRIPTION, ANNOTATION, COMMENTS, ISENABLED, SORTORDER, LOCALEIDENTIFIER, LASTWRITTEN, VERSIONNO) VALUES ('MOLSACertPeriodCode', 'CPC17012', 'Twelve Months', '', '', '1', 0, 'en', CURRENT TIMESTAMP, 1); INSERT INTO FunctionIdentifier (fidName, projectPackage, codePackage, description, fidEnabled) values ('MOLSACalcCertDateRange.calcCertificationDates', 'curam', 'molsa.pd.facade', 'curam.molsa.pd.facade.MOLSACalcCertDateRange.calcCertificationDates', 'Y'); INSERT INTO FunctionIdentifier (fidName, projectPackage, codePackage, description, fidEnabled) values ('MOLSACalcCertDateRange.getCertModifiableInd', 'curam', 'molsa.pd.facade', ' curam.molsa.pd.facade.MOLSACalcCertDateRange.getCertModifiableInd', 'Y'); INSERT INTO SECURITYIDENTIFIER (DESCRIPTION, LASTWRITTEN, SIDNAME, SIDTYPE, VERSIONNO) VALUES (null, null, 'MOLSACalcCertDateRange.calcCertificationDates', 'FUNCTION', 0); INSERT INTO SECURITYIDENTIFIER (DESCRIPTION, LASTWRITTEN, SIDNAME, SIDTYPE, VERSIONNO) VALUES (null, null, 'MOLSACalcCertDateRange.getCertModifiableInd', 'FUNCTION', 0); INSERT INTO SECURITYFIDSID(SIDNAME, FIDNAME, LASTWRITTEN) VALUES ('MOLSACalcCertDateRange.calcCertificationDates', 'MOLSACalcCertDateRange.calcCertificationDates'); INSERT INTO SECURITYFIDSID(SIDNAME, FIDNAME, LASTWRITTEN) VALUES ('MOLSACalcCertDateRange.getCertModifiableInd', 'MOLSACalcCertDateRange.getCertModifiableInd'); INSERT INTO SECURITYGROUPSID (GROUPNAME, LASTWRITTEN, SIDNAME) VALUES ('SUPERGROUP', null, 'MOLSACalcCertDateRange.calcCertificationDates'); INSERT INTO SECURITYGROUPSID (GROUPNAME, LASTWRITTEN, SIDNAME) VALUES ('SUPERGROUP', null, 'MOLSACalcCertDateRange.getCertModifiableInd'); INSERT INTO FunctionIdentifier (fidName, projectPackage, codePackage, description, fidEnabled) values ('MOLSAExpCertCloseCaseBatch.process', 'curam', 'molsa.pd.batch', 'curam.molsa.pd.batch.MOLSAExpCertCloseCaseBatch.process', 'Y'); INSERT INTO FunctionIdentifier (fidName, projectPackage, codePackage, description, fidEnabled) values ('MOLSAExpCertCloseCaseBatchStream.process', 'curam', 'molsa.pd.batch', 'curam.molsa.pd.batch.MOLSAExpCertCloseCaseBatchStream.process', 'Y'); INSERT INTO FunctionIdentifier (fidName, projectPackage, codePackage, description, fidEnabled) values ('MOLSAExpCertSuspendCaseBatch.process', 'curam', 'molsa.pd.batch', 'curam.molsa.pd.batch.MOLSAExpCertSuspendCaseBatch.process', 'Y'); INSERT INTO FunctionIdentifier (fidName, projectPackage, codePackage, description, fidEnabled) values ('MOLSAExpCertSuspendCaseBatchStream.process', 'curam', 'molsa.pd.batch', 'curam.molsa.pd.batch.MOLSAExpCertSuspendCaseBatchStream.process', 'Y'); -- INSERT INTO SECURITYIDENTIFIER (DESCRIPTION, LASTWRITTEN, SIDNAME, SIDTYPE, VERSIONNO) VALUES (null, null, 'MOLSAExpCertCloseCaseBatch.process', 'FUNCTION', 0); INSERT INTO SECURITYIDENTIFIER (DESCRIPTION, LASTWRITTEN, SIDNAME, SIDTYPE, VERSIONNO) VALUES (null, null, 'MOLSAExpCertCloseCaseBatchStream.process', 'FUNCTION', 0); INSERT INTO SECURITYIDENTIFIER (DESCRIPTION, LASTWRITTEN, SIDNAME, SIDTYPE, VERSIONNO) VALUES (null, null, 'MOLSAExpCertSuspendCaseBatch.process', 'FUNCTION', 0); INSERT INTO SECURITYIDENTIFIER (DESCRIPTION, LASTWRITTEN, SIDNAME, SIDTYPE, VERSIONNO) VALUES (null, null, 'MOLSAExpCertSuspendCaseBatchStream.process', 'FUNCTION', 0); -- INSERT INTO SECURITYFIDSID(SIDNAME, FIDNAME, LASTWRITTEN) VALUES ('MOLSAExpCertCloseCaseBatch.process', 'MOLSAExpCertCloseCaseBatch.process'); INSERT INTO SECURITYFIDSID(SIDNAME, FIDNAME, LASTWRITTEN) VALUES ('MOLSAExpCertCloseCaseBatchStream.process', 'MOLSAExpCertCloseCaseBatchStream.process'); INSERT INTO SECURITYFIDSID(SIDNAME, FIDNAME, LASTWRITTEN) VALUES ('MOLSAExpCertSuspendCaseBatch.process', 'MOLSAExpCertSuspendCaseBatch.process'); INSERT INTO SECURITYFIDSID(SIDNAME, FIDNAME, LASTWRITTEN) VALUES ('MOLSAExpCertSuspendCaseBatchStream.process', 'MOLSAExpCertSuspendCaseBatchStream.process'); -- INSERT INTO SECURITYGROUPSID (GROUPNAME, LASTWRITTEN, SIDNAME) VALUES ('SUPERGROUP', null, 'MOLSAExpCertCloseCaseBatch.process'); INSERT INTO SECURITYGROUPSID (GROUPNAME, LASTWRITTEN, SIDNAME) VALUES ('SUPERGROUP', null, 'MOLSAExpCertCloseCaseBatchStream.process'); INSERT INTO SECURITYGROUPSID (GROUPNAME, LASTWRITTEN, SIDNAME) VALUES ('SUPERGROUP', null, 'MOLSAExpCertSuspendCaseBatch.process'); INSERT INTO SECURITYGROUPSID (GROUPNAME, LASTWRITTEN, SIDNAME) VALUES ('SUPERGROUP', null, 'MOLSAExpCertSuspendCaseBatchStream.process'); -- INSERT INTO BatchProcDef (ProcessDefName, AppName, ClassName, OpName) values ('MOLSAExpCertCloseCaseBatch', 'curam', 'MOLSAExpCertCloseCaseBatch', 'process'); INSERT INTO BatchProcDef (ProcessDefName, AppName, ClassName, OpName) values ('MOLSAExpCertCloseCaseBatch', 'curam', 'MOLSAExpCertCloseCaseBatch', 'process'); INSERT INTO BatchProcDef (ProcessDefName, AppName, ClassName, OpName) values ('MOLSAExpCertCloseCaseBatchStream', 'curam', 'MOLSAExpCertCloseCaseBatchStream', 'process'); INSERT INTO BatchProcDef (ProcessDefName, AppName, ClassName, OpName) values ('MOLSAExpCertCloseCaseBatchStream', 'curam', 'MOLSAExpCertCloseCaseBatchStream', 'process'); INSERT INTO BatchParamDef (ProcessDefName, ParamName, ParamType) values ('MOLSAExpCertCloseCaseBatchStream', 'instanceID', 'BATCH_PROCESS_INSTANCE_ID'); INSERT INTO BatchParamDef (ProcessDefName, ParamName, ParamType) values ('MOLSAExpCertCloseCaseBatchStream', 'processingDate', 'CURAM_DATE'); INSERT INTO BatchProcDef (ProcessDefName, AppName, ClassName, OpName) values ('MOLSAExpCertSuspendCaseBatch', 'curam', 'MOLSAExpCertSuspendCaseBatch', 'process'); INSERT INTO BatchProcDef (ProcessDefName, AppName, ClassName, OpName) values ('MOLSAExpCertSuspendCaseBatch', 'curam', 'MOLSAExpCertSuspendCaseBatch', 'process'); INSERT INTO BatchProcDef (ProcessDefName, AppName, ClassName, OpName) values ('MOLSAExpCertSuspendCaseBatchStream', 'curam', 'MOLSAExpCertSuspendCaseBatchStream', 'process'); INSERT INTO BatchProcDef (ProcessDefName, AppName, ClassName, OpName) values ('MOLSAExpCertSuspendCaseBatchStream', 'curam', 'MOLSAExpCertSuspendCaseBatchStream', 'process'); INSERT INTO BatchParamDef (ProcessDefName, ParamName, ParamType) values ('MOLSAExpCertSuspendCaseBatchStream', 'instanceID', 'BATCH_PROCESS_INSTANCE_ID'); INSERT INTO BatchParamDef (ProcessDefName, ParamName, ParamType) values ('MOLSAExpCertSuspendCaseBatchStream', 'processingDate', 'CURAM_DATE'); |  | Note: New entry is added and modified existing entry in applicattion.prx file, require build insertproperties New javascript is added. Navigation file is added that required build inserettabconfiguration
2017-03-03 |  | Modified Existing files ----------------------- \EJBServer\components\MOLSA\clientapps\MolsaManagerAppViews\MOLSAMAPPWorkspaceSection.sec \EJBServer\components\MOLSA\clientapps\MolsaManagerAppViews\MOLSAMAPPWorkspaceSectionShortcuts.properties \EJBServer\components\MOLSA\clientapps\MolsaManagerAppViews\MOLSAMAPPWorkspaceSectionShortcuts.ssp \EJBServer\components\MOLSA\properties\Application.prx \EJBServer\components\MOLSA_ar\clientapps\MolsaManagerAppViews\MOLSAMAPPWorkspaceSection.sec \EJBServer\components\MOLSA_ar\clientapps\MolsaManagerAppViews\MOLSAMAPPWorkspaceSectionShortcuts.ssp Added New file and folders -------------------------- \EJBServer\components\MOLSA\clientapps\MOLSAFinancialScheduleList.properties \EJBServer\components\MOLSA\clientapps\MOLSAFinancialScheduleList.tab \EJBServer\components\MOLSA\codetable\CT_MOLSAFinScheduleStatus.ctx \EJBServer\components\MOLSA\codetable\CT_MOLSAFinancialBatchType.ctx \EJBServer\components\MOLSA\message\MOLSABpoFinancialSchedule.xml \EJBServer\components\MOLSA\model\Packages\Financial\Batch \EJBServer\components\MOLSA\model\Packages\Financial\Batch\Batch.efx \EJBServer\components\MOLSA\model\Packages\Financial\Domain Definition \EJBServer\components\MOLSA\model\Packages\Financial\Domain Definition\DomainDefinition.efx \EJBServer\components\MOLSA\model\Packages\Financial\Entity \EJBServer\components\MOLSA\model\Packages\Financial\Entity\Entity.efx \EJBServer\components\MOLSA\model\Packages\Financial\Facade \EJBServer\components\MOLSA\model\Packages\Financial\Facade\Facade.efx \EJBServer\components\MOLSA\model\Packages\Financial\Financial.efx \EJBServer\components\MOLSA\model\Packages\Financial\ServiceLayer \EJBServer\components\MOLSA\model\Packages\Financial\ServiceLayer\ServiceLayer.efx \EJBServer\components\MOLSA\source\curam\molsa\financial \EJBServer\components\MOLSA\source\curam\molsa\financial\batch \EJBServer\components\MOLSA\source\curam\molsa\financial\batch\impl \EJBServer\components\MOLSA\source\curam\molsa\financial\batch\impl\MOLSAFinancialScheduleBatch.java \EJBServer\components\MOLSA\source\curam\molsa\financial\facade \EJBServer\components\MOLSA\source\curam\molsa\financial\facade\impl \EJBServer\components\MOLSA\source\curam\molsa\financial\facade\impl\MOLSAFinancialSchedule.java \EJBServer\components\MOLSA\source\curam\molsa\financial\sl \EJBServer\components\MOLSA\source\curam\molsa\financial\sl\impl \EJBServer\components\MOLSA\source\curam\molsa\financial\sl\impl\MOLSAMaintainFinancialSchedule.java \EJBServer\MOLSA Financial Batch Schedule Execution.bat \webclient\components\MOLSA\Financial \webclient\components\MOLSA\Financial\MOLSA_cancelFinancialSchedule.properties \webclient\components\MOLSA\Financial\MOLSA_cancelFinancialSchedule.uim \webclient\components\MOLSA\Financial\MOLSA_createNewFinancialSchedule.properties \webclient\components\MOLSA\Financial\MOLSA_createNewFinancialSchedule.uim \webclient\components\MOLSA\Financial\MOLSA_listFinancialSchedule.properties \webclient\components\MOLSA\Financial\MOLSA_listFinancialSchedule.uim | CR 7.2 Financial batches should run more securely | Bhaskar | Yes | -- CREATE TABLE MOLSAFINANCIALSCHEDULE( MOLSAFINANCIALSCHEDULEID BIGINT not null, RUNDATE DATE, RUNMONTH INT not null, RUNYEAR INT not null, BATCHTYPE CHARACTER(10), BATCHSCHEDULESTATUS CHARACTER(10), VERSIONNO INT not null, LASTWRITTEN TIMESTAMP ); -- ALTER TABLE MOLSAFINANCIALSCHEDULE ADD CONSTRAINT MOLSAFINANCIALSCHEDULE PRIMARY KEY(MOLSAFINANCIALSCHEDULEID); -- ONSTRAINT MOLSAFINANCIALSCHEDULE PRIMARY KEY(MOLSAFINANCIALSCHEDULEID); -- INSERT INTO FunctionIdentifier (fidName, projectPackage, codePackage, description, fidEnabled) values ('MOLSAFinancialScheduleBatch.process', 'curam', 'molsa.financial.batch', 'curam.molsa.financial.batch.MOLSAFinancialScheduleBatch.process', 'Y'); INSERT INTO FunctionIdentifier (fidName, projectPackage, codePackage, description, fidEnabled) values ('MOLSAFinancialScheduleBatch.process', 'curam', 'molsa.financial.batch', 'curam.molsa.financial.batch.MOLSAFinancialScheduleBatch.process', 'Y'); INSERT INTO FunctionIdentifier (fidName, projectPackage, codePackage, description, fidEnabled) values ('MOLSAFinancialSchedule.cancelSchedule', 'curam', 'molsa.financial.facade', 'curam.molsa.financial.facade.MOLSAFinancialSchedule.cancelSchedule', 'Y'); INSERT INTO FunctionIdentifier (fidName, projectPackage, codePackage, description, fidEnabled) values ('MOLSAFinancialSchedule.cancelSchedule', 'curam', 'molsa.financial.facade', 'curam.molsa.financial.facade.MOLSAFinancialSchedule.cancelSchedule', 'Y'); INSERT INTO FunctionIdentifier (fidName, projectPackage, codePackage, description, fidEnabled) values ('MOLSAFinancialSchedule.completeSchedule', 'curam', 'molsa.financial.facade', 'curam.molsa.financial.facade.MOLSAFinancialSchedule.completeSchedule', 'Y'); INSERT INTO FunctionIdentifier (fidName, projectPackage, codePackage, description, fidEnabled) values ('MOLSAFinancialSchedule.completeSchedule', 'curam', 'molsa.financial.facade', 'curam.molsa.financial.facade.MOLSAFinancialSchedule.completeSchedule', 'Y'); INSERT INTO FunctionIdentifier (fidName, projectPackage, codePackage, description, fidEnabled) values ('MOLSAFinancialSchedule.createNewCompletedSchedule', 'curam', 'molsa.financial.facade', 'curam.molsa.financial.facade.MOLSAFinancialSchedule.createNewCompletedSchedule', 'Y'); INSERT INTO FunctionIdentifier (fidName, projectPackage, codePackage, description, fidEnabled) values ('MOLSAFinancialSchedule.createNewCompletedSchedule', 'curam', 'molsa.financial.facade', 'curam.molsa.financial.facade.MOLSAFinancialSchedule.createNewCompletedSchedule', 'Y'); INSERT INTO FunctionIdentifier (fidName, projectPackage, codePackage, description, fidEnabled) values ('MOLSAFinancialSchedule.createNewSchedule', 'curam', 'molsa.financial.facade', 'curam.molsa.financial.facade.MOLSAFinancialSchedule.createNewSchedule', 'Y'); INSERT INTO FunctionIdentifier (fidName, projectPackage, codePackage, description, fidEnabled) values ('MOLSAFinancialSchedule.createNewSchedule', 'curam', 'molsa.financial.facade', 'curam.molsa.financial.facade.MOLSAFinancialSchedule.createNewSchedule', 'Y'); INSERT INTO FunctionIdentifier (fidName, projectPackage, codePackage, description, fidEnabled) values ('MOLSAFinancialSchedule.getCurrentMonthScheduleByBatchType', 'curam', 'molsa.financial.facade', 'curam.molsa.financial.facade.MOLSAFinancialSchedule.getCurrentMonthScheduleByBatchType', 'Y'); INSERT INTO FunctionIdentifier (fidName, projectPackage, codePackage, description, fidEnabled) values ('MOLSAFinancialSchedule.getCurrentMonthScheduleByBatchType', 'curam', 'molsa.financial.facade', 'curam.molsa.financial.facade.MOLSAFinancialSchedule.getCurrentMonthScheduleByBatchType', 'Y'); INSERT INTO FunctionIdentifier (fidName, projectPackage, codePackage, description, fidEnabled) values ('MOLSAFinancialSchedule.listSchedule', 'curam', 'molsa.financial.facade', 'curam.molsa.financial.facade.MOLSAFinancialSchedule.listSchedule', 'Y'); INSERT INTO FunctionIdentifier (fidName, projectPackage, codePackage, description, fidEnabled) values ('MOLSAFinancialSchedule.listSchedule', 'curam', 'molsa.financial.facade', 'curam.molsa.financial.facade.MOLSAFinancialSchedule.listSchedule', 'Y'); -- INSERT INTO BatchProcDef (ProcessDefName, AppName, ClassName, OpName) values ('MOLSAFinancialScheduleBatch', 'curam', 'MOLSAFinancialScheduleBatch', 'process'); INSERT INTO BatchProcDef (ProcessDefName, AppName, ClassName, OpName) values ('MOLSAFinancialScheduleBatch', 'curam', 'MOLSAFinancialScheduleBatch', 'process'); -- INSERT INTO CodeTableHeader (TableName, TimeEntered, DefaultCode, LASTWRITTEN, VERSIONNO) VALUES ('MOLSAFinancialBatchType', CURRENT TIMESTAMP, 'FBT17001', CURRENT TIMESTAMP, 1); INSERT INTO CTDISPLAYNAME (TableName, LOCALEIdentifier,TEXT,LASTWRITTEN ) VALUES ( 'MOLSAFinancialBatchType','en','Financial Batch Type', CURRENT TIMESTAMP); INSERT INTO CodeTableItem (TABLENAME, CODE, DESCRIPTION, ANNOTATION, COMMENTS, ISENABLED, SORTORDER, LOCALEIDENTIFIER, LASTWRITTEN, VERSIONNO) VALUES ('MOLSAFinancialBatchType', 'FBT17001', 'Main Batch', '', '', '1', 1, 'en', CURRENT TIMESTAMP, 1); INSERT INTO CodeTableItem (TABLENAME, CODE, DESCRIPTION, ANNOTATION, COMMENTS, ISENABLED, SORTORDER, LOCALEIDENTIFIER, LASTWRITTEN, VERSIONNO) VALUES ('MOLSAFinancialBatchType', 'FBT17002', 'Mid Batch', '', '', '1', 2, 'en', CURRENT TIMESTAMP, 1); -- INSERT INTO CodeTableHeader (TableName, TimeEntered, DefaultCode, LASTWRITTEN, VERSIONNO) VALUES ('MOLSAFinScheduleStatus', CURRENT TIMESTAMP, 'FBS17001', CURRENT TIMESTAMP, 1); INSERT INTO CTDISPLAYNAME (TableName, LOCALEIdentifier,TEXT,LASTWRITTEN ) VALUES ( 'MOLSAFinScheduleStatus','en','Molsa Financial Schedule Status', CURRENT TIMESTAMP); INSERT INTO CodeTableItem (TABLENAME, CODE, DESCRIPTION, ANNOTATION, COMMENTS, ISENABLED, SORTORDER, LOCALEIDENTIFIER, LASTWRITTEN, VERSIONNO) VALUES ('MOLSAFinScheduleStatus', 'FBS17001', 'Active', '', '', '1', 1, 'en', CURRENT TIMESTAMP, 1); INSERT INTO CodeTableItem (TABLENAME, CODE, DESCRIPTION, ANNOTATION, COMMENTS, ISENABLED, SORTORDER, LOCALEIDENTIFIER, LASTWRITTEN, VERSIONNO) VALUES ('MOLSAFinScheduleStatus', 'FBS17002', 'Canceled', '', '', '1', 2, 'en', CURRENT TIMESTAMP, 1); INSERT INTO CodeTableItem (TABLENAME, CODE, DESCRIPTION, ANNOTATION, COMMENTS, ISENABLED, SORTORDER, LOCALEIDENTIFIER, LASTWRITTEN, VERSIONNO) VALUES ('MOLSAFinScheduleStatus', 'FBS17003', 'Executed', '', '', '1', 3, 'en', CURRENT TIMESTAMP, 1); -- INSERT INTO SECURITYIDENTIFIER (DESCRIPTION, LASTWRITTEN, SIDNAME, SIDTYPE, VERSIONNO) VALUES (null, null, 'MOLSAFinancialSchedule.cancelSchedule', 'FUNCTION', 0); INSERT INTO SECURITYIDENTIFIER (DESCRIPTION, LASTWRITTEN, SIDNAME, SIDTYPE, VERSIONNO) VALUES (null, null, 'MOLSAFinancialSchedule.completeSchedule', 'FUNCTION', 0); INSERT INTO SECURITYIDENTIFIER (DESCRIPTION, LASTWRITTEN, SIDNAME, SIDTYPE, VERSIONNO) VALUES (null, null, 'MOLSAFinancialSchedule.createNewCompletedSchedule', 'FUNCTION', 0); INSERT INTO SECURITYIDENTIFIER (DESCRIPTION, LASTWRITTEN, SIDNAME, SIDTYPE, VERSIONNO) VALUES (null, null, 'MOLSAFinancialSchedule.createNewSchedule', 'FUNCTION', 0); INSERT INTO SECURITYIDENTIFIER (DESCRIPTION, LASTWRITTEN, SIDNAME, SIDTYPE, VERSIONNO) VALUES (null, null, 'MOLSAFinancialSchedule.getCurrentMonthScheduleByBatchType', 'FUNCTION', 0); INSERT INTO SECURITYIDENTIFIER (DESCRIPTION, LASTWRITTEN, SIDNAME, SIDTYPE, VERSIONNO) VALUES (null, null, 'MOLSAFinancialSchedule.listSchedule', 'FUNCTION', 0); INSERT INTO SECURITYIDENTIFIER (DESCRIPTION, LASTWRITTEN, SIDNAME, SIDTYPE, VERSIONNO) VALUES (null, null, 'MOLSAFinancialScheduleBatch.process', 'FUNCTION', 0); -- INSERT INTO SECURITYFIDSID(SIDNAME, FIDNAME, LASTWRITTEN) VALUES ('MOLSAFinancialSchedule.cancelSchedule', 'MOLSAFinancialSchedule.cancelSchedule', CURRENT TIMESTAMP); INSERT INTO SECURITYFIDSID(SIDNAME, FIDNAME, LASTWRITTEN) VALUES ('MOLSAFinancialSchedule.completeSchedule', 'MOLSAFinancialSchedule.completeSchedule', CURRENT TIMESTAMP); INSERT INTO SECURITYFIDSID(SIDNAME, FIDNAME, LASTWRITTEN) VALUES ('MOLSAFinancialSchedule.createNewCompletedSchedule', 'MOLSAFinancialSchedule.createNewCompletedSchedule', CURRENT TIMESTAMP); INSERT INTO SECURITYFIDSID(SIDNAME, FIDNAME, LASTWRITTEN) VALUES ('MOLSAFinancialSchedule.createNewSchedule', 'MOLSAFinancialSchedule.createNewSchedule', CURRENT TIMESTAMP); INSERT INTO SECURITYFIDSID(SIDNAME, FIDNAME, LASTWRITTEN) VALUES ('MOLSAFinancialSchedule.getCurrentMonthScheduleByBatchType', 'MOLSAFinancialSchedule.getCurrentMonthScheduleByBatchType', CURRENT TIMESTAMP); INSERT INTO SECURITYFIDSID(SIDNAME, FIDNAME, LASTWRITTEN) VALUES ('MOLSAFinancialSchedule.listSchedule', 'MOLSAFinancialSchedule.listSchedule', CURRENT TIMESTAMP); INSERT INTO SECURITYFIDSID(SIDNAME, FIDNAME, LASTWRITTEN) VALUES ('MOLSAFinancialScheduleBatch.process', 'MOLSAFinancialScheduleBatch.process', CURRENT TIMESTAMP); -- INSERT INTO SECURITYGROUPSID (GROUPNAME, LASTWRITTEN, SIDNAME) VALUES ('SUPERGROUP', null, 'MOLSAFinancialSchedule.cancelSchedule'); INSERT INTO SECURITYGROUPSID (GROUPNAME, LASTWRITTEN, SIDNAME) VALUES ('SUPERGROUP', null, 'MOLSAFinancialSchedule.completeSchedule'); INSERT INTO SECURITYGROUPSID (GROUPNAME, LASTWRITTEN, SIDNAME) VALUES ('SUPERGROUP', null, 'MOLSAFinancialSchedule.createNewCompletedSchedule'); INSERT INTO SECURITYGROUPSID (GROUPNAME, LASTWRITTEN, SIDNAME) VALUES ('SUPERGROUP', null, 'MOLSAFinancialSchedule.createNewSchedule'); INSERT INTO SECURITYGROUPSID (GROUPNAME, LASTWRITTEN, SIDNAME) VALUES ('SUPERGROUP', null, 'MOLSAFinancialSchedule.getCurrentMonthScheduleByBatchType'); INSERT INTO SECURITYGROUPSID (GROUPNAME, LASTWRITTEN, SIDNAME) VALUES ('SUPERGROUP', null, 'MOLSAFinancialSchedule.listSchedule'); INSERT INTO SECURITYGROUPSID (GROUPNAME, LASTWRITTEN, SIDNAME) VALUES ('SUPERGROUP', null, 'MOLSAFinancialScheduleBatch.process'); --